## Sheet1
Recruitment Process | [6 empty] | Search Committee Chair | Search Committee | Responsible Manager | HR Analyst, HR Director or Affirmative Action | Director, Exec Dean | President or Designee
Stage 1
1 | Identify new or vacant position - Dean/ET | [7 empty] | P |  | A | V
2 | Create/edit/review position description - Responsible Mgr/ET; search team | [7 empty] | P | V | A
3 | Responsible Manager selects Search Chair and Committee | [7 empty] | P | V | V
4 | Complete online LEO posting | [5 empty] | P |  | P | V | V
5 | Determine advertising plan - search team participates | [5 empty] | P | P | P | V | V
6 | LEO approval process - led by analyst | [7 empty] | A |  | A
7 | Post - analyst | [8 empty] | A
8 | Advertise - see step 5 | [5 empty] | P | P | P | P | V
9 | Analyst/Dean set up Search Chair Orientation (2.5hrs) | [5 empty] | P |  | V | P
10 | Chair arrange the first Search Committee Orientation - develop timeline | [5 empty] | P |  |  | P
11 | Complete/Submit Search Committee Agreement (before viewing applicants) | [5 empty] | P | P
Chair - immediately send summary e-mail to team with
decisions/confidentiality/ Timeline/ committee assignments
Stage 2 -- This is where the committee can slow down or meet a timeline
12 | COMMITTEE - Develop evaluation components | [5 empty] | P | P | V | V
13 | CHAIR/DEAN/Director -- Submit evaluation components | [5 empty] | P | P | A
14 | ANALYST - Approve evaluation components | [7 empty] | A | A
15 | Position Closes
16 | Affirmative Action Review of Applicant Pool - analyst | [8 empty] | A
Stage 3 - number of applicants could effect time to screen
17 | Paper screening - MQ's & Scoring | [5 empty] | P | P
18 | Review screening results - | [5 empty] | P | P | P | P
19 | Complete recruitment report | [5 empty] | P |  | P | V
20 | Affirmative Action Review of Recruitment Report | [8 empty] | A | V
Stage 4 - Ensure ALL paperwork is submitted or it will slow down your process
21 | Chair/HM - Contact candidates for interviews | [5 empty] | P |  | P
22 | Conduct interviews and other screening components | [5 empty] | P | P | P
23 | Write summary of search committee recommendations | [5 empty] | P |  | P
24 | Conduct reference checks | [5 empty] | P | V | P
25 | Submit all paper copies/committee documents to HR | [5 empty] | P |  | V
26 | Submit Employment Recommendation | [5 empty] | P |  | P |  | A
27 | Analyst analysis and verification of search | [5 empty] | V |  | V | A
28 | Analyst Salary Placement | [8 empty] | A
29 | Affirmative Action Review of Recruitment File | [8 empty] | A
30 | Facilitates signature process (4- 5 signatures needed) | [7 empty] | V | P | V | P
31 | Pres office advise analyst / analyst contacts Dean/Director | [7 empty] | P | P | A | A
32 | Upon Presidential Approval - Offer Job | [7 empty] | P |  | A | A
Key Code:
P | Primary responsibility | V | Advisory | A | Approval | Approval
\\RAINIER\DATA1\HUMANRESOURCES\RECRUITMENT\Current Process Forms\Processes\Recruitment Process_Sept2014.xlsx